Sequence Project Activities

|  |  |  |
| --- | --- | --- |
| **WBS ID** | **Task/Activity Name** | **Predecessor** |
| 1.01 | Identify target office space | -- |
| 1.02 | Negotiate and sign lease | Identify target office space |
| 1.04 | Select new internet provider + backup | Notify internet provider of move |
| 1.05 | Start space remodel (paint, wiring, core drill, carpet…) | Select new internet provider |
| 1.06 | Assemble existing furniture | Space remodel |
| 1.07 | Power existing furniture | Assemble existing furniture |
| 1.08 | Electrical improvements - | Power existing furniture |
| 2.01 | Select vendors for “new” furniture | Electrical improvements |
| 2.015 | Select coffee service vendor | Select vendors |
| 2.02 | Purchase new furniture | Select vendors |
| 2.03 | Assemble new furniture | Purchase new furniture |
| 2.04 | Electrical improvements 2 | Assemble new furniture |
| 2.05 | Hire new employees | Core drills (electrical improvements 2) |
| 2.06 | Purchase IT and office assets/supplies | Hire new employees |
| 2.07 | Select new interns | Purchase IT/office assets and supplies |
| 3.01 | Prep office space and marketing/presentations |  |
| 3.02 | Host kubernetes meetup | Prep office space and marketing materials |
| 3.03 | Prep marketing/presentation for conference | Host meetup |
| 3.04 | Attend conference | Prep marketing/presentations |
| 3.05 | Purchase IT/office supplies and arrange accommodations | Attend conference |
| 3.06 | Exchange engineer arrival | Purchase IT/office supplies and arrange accommodations |
| 3/07 | Show engineers around the city | Exchange engineers arrival |
| 3.08 | Expand scope of existing projects/start new projects | Show engineers around the city |
| 3.09 | Hire new employees | Expand scope of existing project/start new projects |